## Gantchart
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE PERSONALIZED DATA DRIVEN CAREER COUNSELLING MANAGEMENT SYSTEM | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY (CSE DATA SCIENCE)
PROJECT GUIDE PROF. RAJASHRI CHAUDHARI | [6 empty] | DATE | [13 empty] | 2023-04-04
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [39 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Riya, Veena, Sanika, Janvi | 2023-10-01 | 2023-01-24 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Riya, Janvi | 2023-10-01 | 1-17-23 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.3 | Discussing the project topic with the help of paper prototype. | Riya, Sanika, | 1-17-23 | 1-24-23 | 1 | 100% | bar: WEEK 4 M to WEEK 5 F
1.4 | Designing the Graphical User Interface(GUI) | Riya, Janvi, Sanika | 1-24-23 | 2023-07-02 | 2 | 100% | bar: WEEK 5 M to WEEK 7 F
1.5 | Presentation I | Riya, Sanika, Veena, Janvi | 2-14-23 | 2023-06-03 | 2 | 100% | bar: WEEK 8 M to WEEK 8 F
2 | Project Design and Implementation
2.1 | Database Design | Sanika, Riya, Janvi | 2023-06-03 | 3-14-23 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
2.2 | Database Connectivity of all modules | Veena,Janvi | 3-14-23 | 3-21-23 | 2 | 100% | bar: WEEK 10 M to WEEK 11 F
2.3 | Integration of all modules and Report Writing | Riya, Janvi, Sanika, Veena | 3-21-23 | 3-28-23 | 1 | 100%
2.4 | Presentation II | Riya, Sanika, Veena, Janvi | 2023-04-04 | 4-20-23 | 2 | 100% | bar: WEEK 11 M to WEEK 13 F